# Customer support improvement plan

Fictional example for document analysis

The support team will pilot a new intake process to reduce the time customers wait for a first response. The pilot starts on 2 November 2026 and runs for four weeks.

## Goals

Reduce the average first response time from 24 hours to 8 hours. Keep customer satisfaction at or above 90 percent.

## Responsibilities

Maya Chen owns the pilot. Alex Tan will train the support team by 28 October. Priya Lee will publish a weekly dashboard every Friday.

## Risks and next review

The main risk is limited weekend coverage. The team will review staffing after two weeks, on 16 November 2026, and decide whether to extend the pilot.